**AFACT-BMM**

**Plan and timeline**

* Semester A – 2020-21
  + ~~Omer catch up with the rational of the study design~~
  + ~~Omer get familiarized with the BMM task – rational and target~~
  + ~~Discussion with Amit about the possibility to add pre-post Body Maps task as another measure.~~
  + ~~Editing and approving (with Amit) the BMM task’s instructions~~
  + ~~Recording BMM instructions - Pilot~~
  + ~~Finalizing all other tasks’ instructions~~
  + ~~Wrapping the project in a zip file~~
* March-April 2021
  + Finish the remote running
  + Creating remote running protocol
  + Deciding on screening questionnaires (ruminations) and a meaningful cutoff score.
  + Ethics approval
  + BMM programing
* May-June 2021
  + Final Recording BMM instructions
  + Pilot study
  + Recruiting & training a student as a research assistant
* June – Summer 2021
  + Running the experiment