**TODOs:**

**ביחד:**

* חיבור של האתר לניסוי
* חיבור של המפות גוף לקבצי קול של הניסוי
* כתיבת חוברת ניסוי
  + פרוטוקול הרצה וכל המידע על כל המטלות

**תומר:**

* סגירה של כמה פרטים טכניים של המטלות
  + לפי מה שמופיע כאן בפירוט לפי מטלות
* קטאוף
* פסיכוזה ואבדנות

**עומר:**

* אתיקה
* Pre-registration

1. All tasks
   1. ~~Male-Female~~
2. DCT

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Needs to be changes now | change to |  | now its |  |
| DEFAULT\_CATCH\_TRIALS\_RATIO | 0.25 or 1.0/8.0 | | 1.0/8.0 | **?** |

Do practice also at post training, maybe shorter in length

1. BMM
   1. Set time constants to silence time (after instructions stops)
   2. Check the length of BMM and compare to AFACT length, while keeping the same amount of stimuli – ***in the pilot***
   3. Identify about 3 levels of random time between trials interval and convert the task to be time and not buttons presses dependent
2. Choose and implement relevant questionnaires – **OMER**
3. **BMM - make sure to adapt wait times to records**
4. Turn off - ***BMM\_DEBUG\_MODE***

**מטלות לביצוע לפני הרצה**

פרויקט – עמית

* אישורים
  + אישור אתיקה
  + פרק שיטה
  + רישום מוקדם
* גיוס
  + מודעה
  + שאלון סינון
  + פרוטוקול ראיון אובדנות
* צוות וציוד
  + שריון חדר
  + אוזניות
* הקלטות
  + שליחת קישור לאתר הקלטות
  + עריכת קבצי קול
  + הורדת אקסלים
  + יצירת תיקייה לנבדק (אקסלים וקבצי קול במקום הייעודי)
  + הפעלת קוד של עומר
* הרצה במעבדה
  + מילוי בייסליין
  + מילוי שאלוני pre
  + הרצת מטלות
  + מילוי שאלוני post
* עבודה על המטלות
  + הטמעת Emotions rating + הטמעת Body Maps

**Plan and timeline**

* Semester A – 2020-21
  + ~~Omer catch up with the rational of the study design~~
  + ~~Omer get familiarized with the BMM task – rational and target~~
  + ~~Discussion with Amit about the possibility to add pre-post Body Maps task as another measure.~~
  + ~~Editing and approving (with Amit) the BMM task’s instructions~~
  + ~~Recording BMM instructions - Pilot~~
  + ~~Finalizing all other tasks’ instructions~~
  + ~~Wrapping the project in a zip file~~
* March 2021
  + Ethics approval
  + Finish the remote running\*\*
  + Deciding on screening questionnaires (ruminations) and a meaningful cutoff score
  + Building the Screening questionnaires in Qualtrix
  + Recruitment procedure – Sona? Social media? students from every universities
  + Rectangles Categorization Task – programing.
  + BMM programing
  + Final Recording BMM instructions
* April 2021
  + Running protocol – Screening (short phone interview?), STP website, questionnaires, Doodle
  + Pilot study
  + Training a student as a research assistant
* May 2021 – Dec 2021
  + Running the experiment