## Slide 1: EXPERIMENTAL DESIGN

## Slide 2: Missions - Tomer
With Yuval:
  Get MAT code
  Get BMM instructions – from the SESIAT study
    How long is it?
    Can time be changed?
    Programs used?
  Write new instructions
With Iftach:
  Get DCT+STP code
  Get MAB (dct+stp+probe-caught) code
    Fix Liad’s problem
  Get A-FACT (dct+stp+feedback)code
  Get state PANAS Code
    Iftach thinks we used the international version
  Get other questionnaires code
  FFMW?
  Get ethics and consent form template
  What do you think on class screening?
With Liad:
  Does Internal-External really work?
  Get PANAS code
With my-self:
  Approve with Amit the BMM-STP idea.
  Write and approve aims
  Adapt (MAT or new) code to new instructions
  Approve with Amit – MMB adaptation
  Adapt A-FACT to MMB if needed
  Understand and incorporate DAADS questionnaire
  Read Liad’s paper the project directory “Logic” – and understand the logics.
  Create an ad for the experiment

## Slide 3
Recruitment
~300 RRS Questionnaires
Classroom based
Analysis
RRS High (and Low) Third(s)
Lab Appointments
LAB

## Slide 4
STP – MAB
STP - DCT
(Baseline of bias)
Questionnaires Battery
(RRS\PTQ\ER\ DAADS)
STP Recoding
(audio editing)
LAB
STP – A-FACT - DCT
(Training)
STP – DCT
(post-interv)
ONE BACK DICHOTIC
STP
AFACT
STP Recoding
(audio editing)
STP Recoding
(audio editing)
STP – MAB
STP - DCT
(Baseline of bias)
BMM
(Training)
STP – DCT
(post-interv)
ONE BACK DICHOTIC
STP
BMM
STP – MAB
STP - DCT
(Baseline of bias)
STP-DCT
(placebo)
STP – DCT
(post-interv)
ONE BACK DICHOTIC
STP
PLACEBO
Home
Other random half
Random (per subject) half of stp stimuli

## Slide 5: Progress plan
Development
  Trials-sentences repetition - decision
    Implementation
    decision is still needed but implementation is automatic
  Emotional reactivity development
    Data saving
  Dct-replacement task - decision
    implementation
  Tasks fine details, randomisation and sentence amount
    Implementation
    Make code flexible to accepting varying amount of sentences, blocks, trials and repetition
  MAB (Self-Caught) development
    Implementation
  One-back Dichotic development
    Implementation
  BMM measurement – brainstorming, decision (A,Y)
    Present current ideas
    Implementation
  Creating coherent stable flow
    That is group dependent (placebo, BMM, AFACT)
    Implementation
  Cross computers tests
    Develop easy install process
  Sentence recording – decision
    Implement current iftach’s code for recording
    Or – sync with website
    Pay attention to amount of sampled negative and neutral sentences
  Additional questionnaires - decision (A)
    Implementation – in Qualtricks
  Create a protocol

## Slide 6
איזו מטלה מתאמנים עליה – הפחתת אינטראקציית נבדק-מטלה
  מה עושים לdesign:
    שינוי המטלה עליה מתאמנים
      מוטורי
      הגירוי שעליו עושים קטגוריזציה
    להשתמש ב-oneback
    שינוי של להשתמש במטלה אחרת לגמרי- go-nogo.
    אפשרות של שינוי – הגירוי
      שינוי המטלה
      שינוי מוטורי
רנדומיזציה
  שהחלוקה לpre-post משפטים תהיה לפי גם:
    ודומיין – randomization by thought domain.
    עוצמה – לראות שזה לא מתנגש עם דומיין.
פגישה עם ליעד – איזו מטלה מחליפה את dct בזמן האימון

## Slide 7: Design fine details by trials for most tasks
Any task – 1 Block
  Task = 1 Block = 80 trials (40neu/40neg)
  AFACT = 2 Blocks (160 trials)
Practice = 8 all neutral. (window = 4)
  For baseline, for AFACT, for MAB including reals examples (feedback – caught)
  Nature – iftach/amit
Fixation
  1000ms – XXX
AFACT
  Feedback presentation for 3sec  then blank screen for 1.4sec
  Following each feedback a random number of 1 or 2 neutral executive trials
  Bias is calculated out of a maximum of 3 STDs
  Facilitation counts as no bias
SUDS – emotional reactivity
  Should we have them
  Pre-baseline, pre-AFACT, post-AFACT, post-MAB
  Take from Ifatch
Baseline = 80 trials
Training (AFACT) = 160 –in two block (break = 3 minutes)
Post intervention = 80 trials
MAB (self-caught = 40 / probe-caught=80)
  If probe  after half of negs and neutrals
  Presented until answer
  Followed by 1.5sec blank  random number of 1 or 2 neutral trials
Catch trials
  Liad – only at baseline – 10/80

## Slide 8: Sentences Habituation prevention strategies
Limiting number of trials
Exciding the number of exposure
Exciding the number of sentences sampling